## Sheet1
ID | Deliverable | Work Package | Sub-Task | Duration (days) | Predecessor | Resource | Cost | Start Date
1 | D1 - Design & Planning | WP1.1 - Requirements & Feasibility | Kick-off Meeting | 2 | - | Project Manager | 20000 | 2025-06-01 | 2026-04-04
2 | D1 - Design & Planning | WP1.1 - Requirements & Feasibility | Define Scope | 6 | 1 | Project Manager | 30000 | 2025-06-03
3 | D1 - Design & Planning | WP1.1 - Requirements & Feasibility | Stakeholder Approvals | 4 | 2 | Project Manager | 25000 | 2025-06-09 |  | 45809 | 46101
4 | D1 - Design & Planning | WP1.2 - UI/UX Design | Wireframes | 7 | 3 | UX Designer | 40000 | 2025-06-13
5 | D1 - Design & Planning | WP1.2 - UI/UX Design | Prototypes | 14 | 4 | UX Designer | 50000 | 2025-06-20
6 | D1 - Design & Planning | WP1.2 - UI/UX Design | Usability Feedback Review | 5 | 5 | Frontend Developer | 20000 | 2025-07-04
7 | D2 - Development | WP2.1 - Backend Setup | Setup Database | 49 | 6 | Backend Developer | 30000 | 2025-07-09
8 | D2 - Development | WP2.1 - Backend Setup | Develop APIs | 49 | 6 | Backend Developer | 200000 | 2025-07-09
9 | D2 - Development | WP2.1 - Backend Setup | User Authentication | 20 | 7.8 | Backend Developer | 120000 | 2025-08-28
10 | D2 - Development | WP2.2 - Frontend Implementation | Login Screen UI | 14 | 9 | Frontend Developer | 70000 | 2025-09-17
11 | D2 - Development | WP2.2 - Frontend Implementation | Dashboard Interface | 24 | 10 | Frontend Developer | 90000 | 2025-10-01
12 | D2 - Development | WP2.2 - Frontend Implementation | Emergency Button UI | 24 | 10 | Frontend Developer | 60000 | 2025-10-01
13 | D3 - Testing & QA | WP3.1 - Functional Testing | Write Test Cases | 20 | 11.12 | QA Tester | 60000 | 2025-10-25
14 | D3 - Testing & QA | WP3.1 - Functional Testing | Unit Testing | 20 | 13 | Backend Developer | 100000 | 2025-11-14
15 | D3 - Testing & QA | WP3.1 - Functional Testing | Bug Logging | 7 | 14 | QA Tester | 50000 | 2025-12-05
16 | D3 - Testing & QA | WP3.2 - User Acceptance Testing(UAT) | Internal UAT | 14 | 15 | UAT Tester | 40000 | 2025-12-12
17 | D3 - Testing & QA | WP3.2 - User Acceptance Testing(UAT) | User Feedback | 5 | 16 | UAT Tester | 40000 | 2025-12-28
18 | D3 - Testing & QA | WP3.2 - User Acceptance Testing(UAT) | Sign-off of UAT | 2 | 17 | UAT Tester | 40000 | 2026-01-02
19 | D4 - Deployment & Training | WP4.1 - Deployment | App Store Setup | 5 | 18 | DevOps | 20000 | 2026-01-04
20 | D4 - Deployment & Training | WP4.1 - Deployment | Deployment to App Stores | 4 | 19 | DevOps | 24999 | 2026-01-09
21 | D4 - Deployment & Training | WP4.1 - Deployment | Gather Customer Feedback | 5 | 20 | QA Tester | 25000 | 2026-01-13
22 | D4 - Deployment & Training | WP4.2 - User Onboarding | User Manual | 9 | 21 | Frontend Developer | 20000 | 2026-01-18
23 | D4 - Deployment & Training | WP4.2 - User Onboarding | Training Video | 9 | 21 | Frontend Developer | 15000 | 2026-01-18
24 | D4 - Deployment & Training | WP4.2 - User Onboarding | Training Sessions | 5 | 22.23 | Project Manager | 15000 | 2026-01-27
25 | D5 - Maintenance & Support | WP5.1 - Bug Fixes | Post Deployement Bug Testing | 8 | 24 | Backend Developer | 100000 | 2026-02-02
26 | D5 - Maintenance & Support | WP5.1 - Bug Fixes | Review Customer Feedback | 11 | 24 | Developer Team | 15000 | 2026-02-10
27 | D5 - Maintenance & Support | WP5.1 - Bug Fixes | Apply Patches | 7 | 25.26 | QA Tester | 50000 | 2026-02-21
28 | D5 - Maintenance & Support | WP5.2 - Feature Enhancements | Review Customer Suggestions | 5 | 27 | Product Owner | 15000 | 2026-03-01
29 | D5 - Maintenance & Support | WP5.2 - Feature Enhancements | Develop Enhancements | 12 | 28 | Full Dev Team | 50000 | 2026-03-06
30 | D5 - Maintenance & Support | WP5.2 - Feature Enhancements | Deploy Update | 7 | 29 | DevOps | 15000 | 2026-03-18
|  |  |  | 295 |  |  | 1449999